## Change Log - PACCA Vision
PACCA VISION - PLATFORM ENHANCEMENTS & CHANGE LOG
Comparison of System State: Initial / Previous Implementation vs. Current Implementation
# | Feature / Module | Previous State (From What) | Root Cause / Business Issue | Current State (Right Now) | Status & Impact
1 | HIL Review - PDF Viewer Stability | PDF viewer reloaded and flickered every 2-3 seconds, resetting scroll position and disrupting document inspection. | Live workbench was polling document details repeatedly. The backend generates fresh Azure SAS security tokens on each call, which changed the iframe URL and forced the browser to re-mount the viewer. | Disabled background polling during active review. Added strict memoization and URL-freezing keyed by documentId so the PDF loads once and never re-renders during review. | RESOLVED (Production Ready) No reload flicker; stable reviewer experience
2 | HIL Review - Layout & Workspace Space | 50% / 50% split layout between the PDF viewer and field sidebar. The PDF view felt cramped, narrow, and congested. | Reviewers require maximum visual clarity on multi-page healthcare documents while field inputs only need standard width. | Redesigned to a premium 75% / 25% layout: 75% full-width area for the document preview and 25% for a streamlined field inspection sidebar. | COMPLETED Significantly improved ergonomics for client staff
3 | HIL Review - AI Summary Component | A large AI Summary card was placed prominently in the review panel, consuming vertical space and pushing extracted fields down. | Client review staff found the card redundant for transactional document verification, cluttering their primary workflow. | Removed the AI summary card from the HIL workbench to give immediate visual priority to field extraction and verification gates. | COMPLETED Clean, clutter-free reviewer workspace
4 | Document Navigation & Smart Routing | All documents opened in the same generic view regardless of their status; documents needing human review were not routed properly. | Staff had to manually determine whether a document needed review or was already completed. | Added conditional routing: documents with 'Needs Review' or 'Failed' status route directly to the HIL Review Workbench. Documents with 'Processed' status open in a clean, view-only document viewer. | COMPLETED Automated workflow routing based on processing state
5 | Real-time Counts & Notification Badges | Header notification badge was hardcoded to '12', and the sidebar HIL tab badge was hardcoded to '(27)'. | Mock static badge counters did not reflect actual queue volume or real backend document states. | Connected badges to real-time document queue computation: dynamically calculates pending items (Needs Review + Failed) and updates notification and HIL counters in real time. | COMPLETED Accurate real-time operational metrics
6 | Live Document Queue (Senderra IDP) | Documents relied on mock static data or expired external links (manus-storage) that failed in live environments. | No direct synchronization with active backend processing pipeline. | Fully integrated with live Senderra IDP API endpoints (/api/senderra/documents), streaming live document queues, statuses, confidence scores, and valid Azure SAS links. | COMPLETED Full real-time backend pipeline synchronization
7 | Solutions Workbench & Schema Management | Used legacy Solutions V1 interface with static schema tables, no field categorization, and broken function imports on Vercel. | Solution developers could not classify healthcare schema fields or push analyzer changes directly to the cloud repository. | Upgraded to Solutions V2: left-sidebar + right-panel layout, field classification dropdowns (Patient, Provider, Clinical, Financial, Administrative), schema validation gates, and direct GitHub sync to senderra-idp-sol. | COMPLETED Full schema lifecycle management with Git sync
8 | Role-Based Access Control (RBAC) | Generic roles with inconsistent permissions across navigation and views. | Need for distinct user personas in production healthcare environments. | Standardized 3 core roles: PACCA Platform Admin, Solution Developer, and Client Staff with tailored navigation, editing rights, and role switcher. | COMPLETED Enterprise persona-based access enforcement